## Slide 1
PROGRAMME CLOSE-OUT
Project
Culmination
Chronicle
A documented account of participation, progress, and possibility from the 2024 Learning Forward programme.
FINAL REPORT · JAN–AUG 2024
Prepared by the Impact & Learning Office
Notes: Cover slide for the Project Culmination Chronicle close-out report.

## Slide 2
01 / THE STORY SO FAR
Executive summary
The 2024 Learning Forward programme concludes with strong evidence of reach, relevance, and readiness for the next chapter.
✓
PROGRAMME OUTCOME
The programme did more than deliver training. It created a practical, shared language for change.
Across six cohorts, the programme supported 171 learners through a blended learning journey combining facilitated sessions, peer exchange, and workplace application.
TARGET EXCEEDED
INDEPENDENT CLOSE-OUT
171
learners reached
94%
completion rate
91%
satisfaction
01
Reach
Every planned cohort was reached, with expanded participation through targeted outreach.
02
Relevance
Learners linked the content to daily work and reported immediate practical value.
03
Readiness
Stakeholders identified clear opportunities to sustain peer learning.
Notes: Executive summary: six cohorts, 171 learners, 95% attendance, and 94% completion.

## Slide 3
01 / THE STORY SO FAR
Programme at a glance
A simple view of the scale, investment, and delivery footprint behind the close-out story.
6
learning cohorts
171
learners reached
24
partner organisations
18
facilitators & speakers
95%
average attendance
R1.24m
actual expenditure
A blended learning journey
Facilitated sessions → peer exchange → workplace application → reflection

## Slide 4
02 / WHO SHOWED UP
Attendance statistics & registers
Participation remained consistent throughout the programme, with an overall attendance rate of 95% against a target of 90%.
ATTENDANCE OVERVIEW
95%
overall attendance
Cohort A
93%
Cohort B
97%
Cohort C
90%
Cohort D
97%
Cohort E
96%
Cohort F
96%
All cohorts met or exceeded the programme attendance threshold.
SIGNED ATTENDANCE REGISTER
Session-level verification record
COHORT | SESSION DATE | PLANNED | PRESENT | STATUS
Cohort A | 12 Mar 2024 | 28 | 26 | Verified
Cohort B | 15 Apr 2024 | 32 | 31 | Verified
Cohort C | 21 May 2024 | 30 | 27 | Verified
Cohort D | 18 Jun 2024 | 30 | 29 | Verified
Cohort E | 16 Jul 2024 | 28 | 27 | Verified
Cohort F | 13 Aug 2024 | 26 | 25 | Verified
Original signed registers are filed in the programme evidence repository and available for audit review.

## Slide 5
03 / VOICES FROM THE PROGRAMME
Stakeholder participation & learner feedback
The strongest signal from the close-out is not only who participated, but how participants describe the value of the experience.
PARTICIPATION SNAPSHOT
171
learners enrolled
24
partner organisations
18
facilitators & speakers
6
learning cohorts
LEARNER FEEDBACK
n = 143 responses
Content relevance
92%
Facilitator quality
96%
Practical application
89%
Materials & support
87%
Respondents rated their experience on a five-point scale. Percentages reflect positive and very positive responses.

## Slide 6
03 / VOICES FROM THE PROGRAMME
What participants carried forward
Learner and partner reflections point to practical value, confidence, and a stronger shared language for change.
“
I left each session with something I could use immediately. The peer examples made the theory feel real.
LEARNER, COHORT D
“
The programme gave our team a shared framework and the confidence to start conversations we had been avoiding.
PARTNER ORGANISATION REPRESENTATIVE
“
The most valuable part was seeing how others solved similar problems. It made progress feel possible.
LEARNER, COHORT B

## Slide 7
04 / THE PROGRAMME IN FOCUS
Media coverage & evidence
A curated record of the people, places, and moments that shaped the programme.
STORIES WORTH CARRYING FORWARD
The programme generated a rich collection of visual and written evidence.
From session photographs to learner reflections and partner stories, the evidence captures more than delivery — it captures movement.
42
photographic evidence
06
video interviews
11
press & web mentions
MEDIA COVERAGE
↗
The Learning Review
Feature article
18 Aug 2024
↗
Community Voice FM
Radio interview
06 Aug 2024
↗
Impact Matters
Programme spotlight
29 Jul 2024
Photographs, video interviews, and published coverage are filed in the programme evidence repository.

## Slide 8
05 / STEWARDSHIP
Financial reconciliation
Programme expenditure was managed within approved parameters, with clear alignment between investment and delivery.
FINAL POSITION
Total approved budget
R1,250,000
Actual expenditure
R1,237,450
99% UTILISED
Unspent balance: R12,550, returned in line with funding conditions.
RECONCILED EXPENDITURE
Learning delivery & facilitation
R534,800
Learner support & materials
R286,450
Monitoring, evaluation & learning
R161,250
Travel & access support
R148,500
Communications & media
R106,450
All line items are supported by invoices, approvals, and payment records.

## Slide 9
06 / LOOKING AHEAD
Lessons learnt
The close-out creates a practical bridge between what worked, what we would change, and what should happen next.
01
Keep the practice close
The strongest learning happened when concepts were immediately connected to a participant's real work. Protect time for application and reflection.
02
Design for the whole system
Partner participation improved relevance and reduced duplication. Bring organisational stakeholders into the design conversation earlier.
03
Make peer learning visible
Informal peer exchange became a defining strength. A simple structure for continued connection would extend the programme's value.
RECOMMENDATION
Invest in the continuation, not just the conclusion.

## Slide 10
CLOSING NOTE
The work continues.
The evidence from this programme points to a clear next step: keep the network connected, deepen workplace application, and make the learning visible beyond the funded period.
Thank you
Impact & Learning Office · August 2024
Notes: Closing slide with the final recommendation and acknowledgement.